## Observing Checklist
Keck/LRIS Oct 6, 2026 Observing Checklist
Task | Done | Notes
Dome open
Telescope tracking
Focus achieved
Guider configured
Dichroic in place
Gratings verified
Standard star (evening)
Science targets started
Standard star (morning)
Arc lamp calibrations
Flat field calibrations
Dome closed
Data transferred
LRIS Configuration
Dichroic | 560
Blue Grism | 600/4000
Red Grating | 600/7500 (centered ~7200 A)
Blue CCD binning | 2x2
Red CCD binning | 2x2
Slit width | 1.0"

## October 6th
Start (LST) | Start (UT) | Start (HST) | Duration | End (HST) | Action | target | RA | DEC | HA start | HA end | mag(r) | red side | blue side | Airmass | Comments
19.9h | 5.2 | 19:10 | 5 min | 19:15 | Flux Standard | BD28d4211 | 21:51:11.02 | +28:51:50.4 | -2.0h | -1.9h | 10.5 | 1 x 30 | 1 x 30 |  | Evening standard
19.9h | 5.2 | 19:15 | 5 min | 19:20 | Focus check
20.2h | 5.5 | 19:29 | 5 min | 19:34 | slew to | FRB20260502A
20.3h | 5.6 | 19:34 | 60 min | 20:34 | Science (MOS) | FRB20260502A | 18:33:56.81 | 46:51:41.4 | +1.7h | +2.7h | 22.4 | MOS mask required | MOS mask required | 1.18 | MASK REQUIRED ¦ CHIME-Unbiased
21.3h | 6.6 | 20:34 | 5 min | 20:39 | slew to | FRB20250408A
21.3h | 6.7 | 20:39 | 53 min | 21:32 | Science | FRB20250408A | 21:11:15.21 | 77:17:32.8 | +0.2h | +1.0h | 21.0 | 3 x 1060 | 3 x 1060 | 1.87 | CHIME-Repeater
22.2h | 7.5 | 21:32 | 5 min | 21:37 | slew to | FRB20260102A
22.3h | 7.6 | 21:37 | 60 min | 22:37 | Science (MOS) | FRB20260102A | 01:56:29.02 | 13:51:58.5 | -3.6h | -2.6h | 21.2 | MOS mask required | MOS mask required | 1.01 | MASK REQUIRED ¦ CHIME-Blind
1.9h | 11.2 | 01:09 | 20 min | 01:29 | slew to | FRB20260418B
2.2h | 11.5 | 01:29 | 19 min | 01:48 | Science | FRB20260418B | 06:11:02.72 | 39:21:33.4 | -4.0h | -3.7h | 20.2 | 3 x 380 | 3 x 380 | 1.09 | CHIME-Lowz
2.9h | 12.2 | 02:14 | 5 min | 02:19 | slew to | FRB20240106A
3.0h | 12.3 | 02:19 | 60 min | 03:19 | Science (MOS) | FRB20240106A | 06:43:36.02 | 60:21:01.5 | -3.7h | -2.7h | 22.5 | MOS mask required | MOS mask required | 1.38 | MASK REQUIRED ¦ CHIME-Blind,CHIME-HighDM
4.0h | 13.3 | 03:19 | 5 min | 03:24 | slew to | Feige110
4.1h | 13.4 | 03:24 | 5 min | 03:29 | Flux Standard | Feige110 | 23:19:58.40 | -05:09:56.2 | +4.8h | +4.9h | 11.8 | 1 x 30 | 1 x 30 |  | Morning standard
4.2h | 13.5 | 03:29 | 10 min | 03:39 | Arc lamps (HgNeArCdZn)
4.4h | 13.7 | 03:39 | 10 min | 03:49 | Internal flats
NOTES:
- Gap from ~22:37-01:09 HST: no further observable targets in hand
- All targets observable at airmass < 2.0 when scheduled
- Keck slews: 5 min base; 20 min when moving from Dec < +20 to Dec > +20
- LRIS setup: 560 dichroic, 600/4000 blue grism, 600/7500 red grating (~7200A)
- Exposure times from the real LRIS ETC (etc.ucolick.org): S/N=10/pixel per single exposure, 3 exposures min
- MOS (mag>21) targets need ~1-2h once masked (see info column); utilization is target-count-limited: request more targets